## product backlog
ID | Theme | Title | As a/an | I want to | so that… | Notes | Priority | Status
1 | User Management |  | Administrator | see all the login attempts (successful and unsuccessful) | I have a better control over who uses my application | log attempts in database and send via email when an error (or above) happens | (3) High | (3) Completed
2 | User Management |  | User | be able to login with my Google credentials | it is easier for me to login without having to remember different usernames/passwords | firt only with Gmail | (2) Medium | (1) Not started
4 | Non functional |  |  | redesign code using the MVC pattern |  | code was restructured (MVT pattern) |  | (3) Completed
5 | Non functional |  |  | add web application browser testing |  | maybe using selenium |  | (1) Not started
6 | Non functional |  |  | use resource strings for text |  | internationalization |  | (3) Completed
7 | User Management | User permissions management | Administrator |  |  |  |  | (3) Completed
8 |  |  |  | to properly insert the organizational chart in the database |  |  |  | (3) Completed
9 | User Management |  |  | login and use the application only if I am activated |  |  |  | (3) Completed
10 |  |  |  | Fix form fields in user edit form. They show None |  |  |  | (3) Completed
11 |  |  |  | to see pdf reports for employees per department etc.
12 |  |  |  | setup virtual environment for the app | it can be uploaded and run from servers |  |  | (3) Completed
13 |  |  |  | do some performance profiling for the application | it can be optimized | http://docs.sqlalchemy.org/en/rel_1_0/faq/performance.html#faq-how-to-profile
14 |  |  |  | improve code design usign design patterns |  |  |  | (3) Completed
15 |  |  |  | Add irs number field to organization
16 |  |  |  | Add constraints and messages to deletions (eg in organizations that have parent organizations)
17 |  |  |  | add photo for users
18 |  |  |  | add logo for organizations
19 |  |  |  | delete View button on user form. Rename Επεξεργασία to Προβολή/Επεξεργασία
20
21
22
23
24

## sprint backlog
ID | Theme | Title | As a/an | I want to | so that… | Notes | Priority | Status | Duration
15 |  |  |  | Add irs number field to organization
17 |  |  |  | add photo for users
18 |  |  |  | add logo for organizations

## Parameters
Priority | User story status
(1) Low | (1) Not started
(2) Medium | (2) In Progress
(3) High | (3) Completed
(4) Postponed